### Figure 3. Practice QI Team Meeting 2 Agenda

Attending: Insert names of attendees here

- (5 minutes) Provide a vision for the quality improvement project. What new thoughts do you have about this after completing your baseline practice assessment?

- (15 minutes) Review your baseline assessment results in the Tool to Schedule Implementation Meetings and Create Practice Goals, “Crosswalk Output” tab

- (60 minutes) Draft specific, measurable goals (STEP 4, page 4)

  - Review goals in the Tool to Schedule Implementation Meetings and Create Practice Goals, “Goal Ideas” and “Final Goal” tabs

  - Use your starting goals document prepared in advance of the meeting to finalize goal selection

  - Refine goals to customize them for your practice and assure that they are specific and measurable

  - Define the priority of accomplishing the goal in case there is limited time or cost considerations

- (10 minutes) Identify Practice QI Team members to

  - Finalize the goals document after the meeting

  - Develop a first draft practice workflow for QI Team meeting 3 (STEP 5, page 5)

  - Begin customizing the Practice Training on Perinatal Mental Health Care Workflow Template

Resources

- Instructions (page 4)

- The starting draft of your own practice-specific goals, prepared in advance

- Aims (page ii)

    - Your practice’s Tool to Schedule Implementation Meetings and Create Practice Goals, “Crosswalk Output”, “Goal Ideas”, and “Final Goals” tabs

- The Aim, Sub-Aims, and Goals document from the Implementation Materials Packet

Next Steps

      - Prepare a final goal document as described in Task 4, item 3  of the Instructions for Completing Assessments (page 31)

      - Prepare a first draft practice workflow (STEP 5, page 4)

      - Let practice personnel know what you found in your baseline assessment – practice strengths and challenges

      - Check how your obstetric care clinicians and clinical staff are progressing in completing the eModule trainings (accessible from the ACOG website in 2023)

      - Integrate your final practice goals into the Practice Training on Perinatal Mental Health Care Workflow Template