### Figure 4. Practice QI Team Meeting 3 Agenda

Attending: Insert names of attendees here

- (80 minutes) Complete STEP 5: Review draft workflow, revise, and refine

- (10 minutes) Identify your QI Team member who will complete each of the following tasks during the next several weeks:

  - Finalize your practice perinatal mental health workflow

  - Send your practice Tool to Schedule Implementation Meetings and Create Practice Goals, and your finalized practice goals and workflow to Lifeline for Moms Team one week before Implementation Consultation meeting 2

  - Develop a starting draft of tasks/roles and responsibilities (STEP 7) using table 8 (page 24) and table 9 (page 26). Table 9 is also included in the Implementation Materials Packet

  - Continue updating the Practice Training on Perinatal Mental Health Care Workflow Template with your practice workflow

Resources Needed

    - Instructions pages 4-5

    - Perinatal Mental Health Practice Workflow Worksheet (Figure 5, pages 53-61)

    - Figure 6. Workflow for Perinatal Mental Health Care (Figure 6, pages 61 and 62 and a single editable copy included in the Implementation Materials Packet)

    - Your practice starting draft perinatal mental health workflow

Next Steps

- Finalize your practice-specific workflow

- Integrate your final workflow into your draft Practice Training on Perinatal Mental Health Care Workflow Template

- Create a starting draft of the Goals and Tasks document (table 8 (page 24) and table 9 (page 26); Table 9 is also included in the Implementation Materials Packet

- Let practice personnel know what goals you have set for your practice